## SFP3 RFP Schedule Template 2026
[5 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | August
[7 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Project Elements | Section | Task | Start Date | End Date | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
Mobilization | 4.6.1 | Mobilization | 2026-05-01
Mobilization | 4.6.2 | Fire Safety | 2026-05-01
Mobilization | 4.6.3 | Dust Abatement | 2026-05-01
Wood Harvest and Transport | 4.1.1 | Transport Decked Wood | 2026-05-04
Wood Harvest and Transport | 4.1.2 | Harvest Wood in floodplain | 2026-05-04
Floodplain Restoration | 4.2.1 | Install staging areas, roads, erosion BMPs | 2026-05-04
Floodplain Restoration | 4.2.2 | Vegetation Clearing & IVM Mastication | 2026-05-04 | 2025-06-15
Floodplain Restoration | 4.2.3 | Cut & Fill (In the Dry) | 2026-05-04
Floodplain Restoration | 4.2.3 | Cut & Fill (In-Water Work) | 2026-06-01
Floodplain Restoration | 4.2.4 | Wood Placement
Floodplain Restoration | 4.2.5 | Water Diversions & Fish Salvage
Floodplain Restoration |  | Final Closeout & Rewatering
Delta Road Decommissioning | 4.3.1 | Bridge Removal
Delta Road Decommissioning | 4.3.2 | Culvert Removal
Delta Road Decommissioning | 4.3.3 | Trail Conversion
Delta Road Decommissioning | 4.3.4 | Road Subsoiling
Road Use | 4.4.0 | Road Use
Rehabilitation | 4.5.0 | Seeding & Erosion Control
Rehabilitation | 4.5.0 | Road & Site Rehabilitation
Mobilization | 4.6.1 | Demobilization |  | 2026-08-21